## Slide 1
VeCAD Elite 2026
Embedded System - ST Edge AI Group
10-day Project Diary
TinyML Occupancy Estimation Prototype
Ahmed Mohamed Abdalla Ahmed
A24KE0429
Notes: Project diary reconstructed from the supplied 10-day PDF template and the student's recorded progress.

## Slide 2
10-day Project Record
From MCU bring-up to a validated data-collection pipeline
DAY 1
Foundation and System Design
Confirmed the MCU and development environment were working.
DAY 2
Component and I2C Planning
Completed the component list and identified the expected device addresses.
DAY 3
STM32 AI Workflow
Understood that training occurs on the computer while inference runs on the STM32.
DAY 4
MNIST Deployment Study
Gained practical familiarity with the full PC-to-MCU inference workflow.
DAY 5
Hardware Preparation and Soldering
Prepared the physical modules for individual electrical testing.
DAY 6
Sensor Bring-Up
Validated the basic drivers and confirmed live readings on the OLED and serial output.
DAY 7
BH1750 Fault Diagnosis
Confirmed that the original GY-302 did not acknowledge on either controller.
DAY 8
VL53L0X Validation
Obtained stable Status 0 measurements for close targets.
DAY 9
Full Hardware Integration
Detected BH1750 0x23, VL53L0X 0x29, OLED 0x3C and BME280 0x76 together.
DAY 10
Data Logger Quality Review
Completed an end-to-end path from STM32 sensors to saved CSV data.
10-day Project Diary | Ahmed Mohamed Abdalla Ahmed | A24KE0429
2
Notes: Overview of the ten recorded workdays. Source: user-supplied project history.

## Slide 3
Day 1
Foundation and System Design
Tasks
Reviewed the NUCLEO-L476RG architecture, memory, clock and header pinout.
Installed STM32CubeIDE and STM32CubeMX, then verified the board with a Blink test.
Defined the system architecture and mapped the sensors, controls and indicators.
Learning Sources and Tools
ST NUCLEO-L476RG documentation
STM32CubeIDE and STM32CubeMX getting-started guides
I2C addressing, voltage levels and pull-up fundamentals
Achievement
Confirmed the MCU and development environment were working.
Completed an initial circuit and pin-assignment plan for the occupancy prototype.
Problem and Engineering Decision
Verified shared-bus addressing and 3.3 V / 5 V compatibility before assembly.
IMAGE / EVIDENCE PLACEHOLDER
Insert the Blink test, NUCLEO board photo or circuit schematic
Day 1 of 10 | Ahmed Mohamed Abdalla Ahmed | A24KE0429
3
Notes: Source: user-supplied project history and captured serial/build outputs.

## Slide 4
Day 2
Component and I2C Planning
Tasks
Ordered the required sensors and supporting components.
Studied the interfaces of BME280, BH1750, VL53L0X, PIR and SSD1306 OLED modules.
Planned one shared I2C bus and dedicated GPIO connections.
Learning Sources and Tools
Sensor datasheets and module pinouts
I2C seven-bit addresses and HAL shifted addresses
Tutorials for individual sensor bring-up
Achievement
Completed the component list and identified the expected device addresses.
Used the delivery period to reduce integration risk before wiring the hardware.
Problem and Engineering Decision
Components required several days to arrive, so software and protocol research continued in parallel.
IMAGE / EVIDENCE PLACEHOLDER
Insert the component list, order summary or final pin map
Day 2 of 10 | Ahmed Mohamed Abdalla Ahmed | A24KE0429
4
Notes: Source: user-supplied project history and captured serial/build outputs.

## Slide 5
Day 3
STM32 AI Workflow
Tasks
Studied TinyML and the role of STM32Cube.AI / X-CUBE-AI.
Mapped the path from labelled sensor data to model training and embedded inference.
Explored model analysis, memory reporting and C code generation in STM32CubeMX.
Learning Sources and Tools
STM32Cube.AI workflow and documentation
TensorFlow / Keras model training basics
MCU memory and computation constraints
Achievement
Understood that training occurs on the computer while inference runs on the STM32.
Defined a future workflow for converting the occupancy model into embedded C code.
Problem and Engineering Decision
The AI toolchain was new, so this day focused on terminology, model formats and deployment steps.
IMAGE / EVIDENCE PLACEHOLDER
Insert an X-CUBE-AI configuration or model-analysis screenshot
Day 3 of 10 | Ahmed Mohamed Abdalla Ahmed | A24KE0429
5
Notes: Source: user-supplied project history and captured serial/build outputs.

## Slide 6
Day 4
MNIST Deployment Study
Tasks
Followed a reference MNIST handwritten-digit CNN project for STM32.
Reviewed Keras training, .h5 import, X-CUBE-AI analysis and code generation.
Compared its NUCLEO-F411RE setup with the target NUCLEO-L476RG platform.
Learning Sources and Tools
Szu-Chi: Implement MNIST Classification on MCU
TensorFlow / Keras CNN workflow
Virtual COM Port testing on an MCU
Achievement
Gained practical familiarity with the full PC-to-MCU inference workflow.
Used the project as a learning reference, not as the final occupancy model.
Problem and Engineering Decision
The reference used a different STM32 board and software versions, so direct reuse required adaptation.
IMAGE / EVIDENCE PLACEHOLDER
Insert the model graph, X-CUBE-AI Analyze page or test output
Day 4 of 10 | Ahmed Mohamed Abdalla Ahmed | A24KE0429
6
Notes: Source: user-supplied project history and captured serial/build outputs.
Reference: https://github.com/Szu-Chi/Implement-MNIST-Handwritten-Digit-Classification-on-MCU

## Slide 7
Day 5
Hardware Preparation and Soldering
Tasks
Inspected the delivered modules and identified headers that required soldering.
Arranged soldering tools and assembled the sensor modules.
Checked pin labels, continuity, supply polarity and header joints.
Learning Sources and Tools
Through-hole soldering and continuity checks
Module power and signal-pin verification
Breadboard wiring practices
Achievement
Prepared the physical modules for individual electrical testing.
Reworked weak joints that could create intermittent I2C communication.
Problem and Engineering Decision
The modules were not ready to plug in immediately, which added soldering and inspection time.
IMAGE / EVIDENCE PLACEHOLDER
Insert a soldering photo or continuity-test result
Day 5 of 10 | Ahmed Mohamed Abdalla Ahmed | A24KE0429
7
Notes: Source: user-supplied project history and captured serial/build outputs.

## Slide 8
Day 6
Sensor Bring-Up
Tasks
Tested the SSD1306 OLED and BME280 through I2C.
Verified UART output and used an I2C scanner to confirm device responses.
Tested PIR inputs, push buttons, LEDs and the active buzzer as GPIO devices.
Learning Sources and Tools
STM32 HAL I2C and GPIO functions
Serial Monitor debugging at 115200 baud
Isolated testing before system integration
Achievement
Validated the basic drivers and confirmed live readings on the OLED and serial output.
Confirmed the active buzzer logic: PB4 LOW produces sound and HIGH is silent.
Problem and Engineering Decision
Resolved several pin, port and power mistakes by testing one module at a time.
IMAGE / EVIDENCE PLACEHOLDER
Insert the OLED readings, GPIO test or Serial Monitor output
Day 6 of 10 | Ahmed Mohamed Abdalla Ahmed | A24KE0429
8
Notes: Source: user-supplied project history and captured serial/build outputs.

## Slide 9
Day 7
BH1750 Fault Diagnosis
Tasks
Scanned the expected BH1750 addresses 0x23 and 0x5C on STM32 and Arduino.
Checked 3.3 V supply, SDA/SCL idle levels, soldering and the ADDR connection.
Compared the module with known-good I2C devices and replacement BH1750 boards.
Learning Sources and Tools
Cross-platform fault isolation
BH1750 raw-data to lux conversion
Separating wiring, software and hardware faults
Achievement
Confirmed that the original GY-302 did not acknowledge on either controller.
Verified a replacement at 0x23 and obtained valid lux readings.
Problem and Engineering Decision
Diagnosed a faulty module only after eliminating code, wiring, address and soldering causes.
IMAGE / EVIDENCE PLACEHOLDER
Insert the failed scan beside the replacement 0x23 / lux output
Day 7 of 10 | Ahmed Mohamed Abdalla Ahmed | A24KE0429
9
Notes: Source: user-supplied project history and captured serial/build outputs.

## Slide 10
Day 8
VL53L0X Validation
Tasks
Integrated the ST VL53L0X API and STM32 HAL platform layer.
Removed Windows-only communication files and corrected build errors.
Logged distance, range status, signal rate and ambient rate.
Learning Sources and Tools
VL53L0X API initialization and calibration
RangeStatus interpretation
Embedded build-error diagnosis
Achievement
Obtained stable Status 0 measurements for close targets.
Displayed live distance data on the OLED and Serial Monitor.
Problem and Engineering Decision
Observed 8190 mm / Status 4 when the target was outside the practical range or narrow field of view.
IMAGE / EVIDENCE PLACEHOLDER
Insert a valid distance test and an 8190 mm / Status 4 example
Day 8 of 10 | Ahmed Mohamed Abdalla Ahmed | A24KE0429
10
Notes: Source: user-supplied project history and captured serial/build outputs.
Reference: https://www.st.com/resource/en/datasheet/vl53l0x.pdf

## Slide 11
Day 9
Full Hardware Integration
Tasks
Connected four I2C devices on the same bus and verified their addresses.
Integrated two PIR sensors, two buttons, two LEDs and the active buzzer.
Added EMPTY, LOW and HIGH labels with button and LED feedback.
Learning Sources and Tools
Multi-device I2C integration
Button debounce and non-blocking buzzer control
System-level power and wiring checks
Achievement
Detected BH1750 0x23, VL53L0X 0x29, OLED 0x3C and BME280 0x76 together.
Ran all sensors and user controls in one STM32 application.
Problem and Engineering Decision
A weak supply/wiring connection initially hid the BME280, then a corrected connection restored the full bus.
IMAGE / EVIDENCE PLACEHOLDER
Insert the assembled prototype or four-device I2C scan
Day 9 of 10 | Ahmed Mohamed Abdalla Ahmed | A24KE0429
11
Notes: Source: user-supplied project history and captured serial/build outputs.

## Slide 12
Day 10
Data Logger Quality Review
Tasks
Built a serial CSV logger with labelled EMPTY, LOW and HIGH sessions.
Used physical controls to select labels and start or stop recording.
Ran a 206-row pilot and applied data-quality checks.
Learning Sources and Tools
Structured data collection and session labelling
Raw-data preservation and validation flags
Sensor suitability assessment before AI training
Achievement
Completed an end-to-end path from STM32 sensors to saved CSV data.
The first review accepted 44 rows and rejected 162, mainly because of invalid ToF measurements.
Problem and Engineering Decision
PIR reports motion rather than continuous presence, while the current VL53L0X range and field of view do not cover a ceiling-mounted room setup.
IMAGE / EVIDENCE PLACEHOLDER
Insert the CSV file, pilot summary or sensor-validity chart
Day 10 of 10 | Ahmed Mohamed Abdalla Ahmed | A24KE0429
12
Notes: Source: user-supplied project history and captured serial/build outputs.

## Slide 13
Final Achievement
A working integrated prototype with an evidence-based plan for the next iteration
Completed
Brought up the NUCLEO-L476RG and implemented the required I2C and GPIO drivers.
Integrated environmental, light, distance and motion sensing with OLED feedback.
Built labelled session controls and a PC logger that saves structured CSV data.
Validated by Evidence
Four devices detected on one I2C bus.
Live values displayed and transmitted at 115200 baud.
A 206-row pilot exposed data-quality limits before model training.
IMAGE / EVIDENCE PLACEHOLDER
Insert the final prototype photo or system block diagram
Next Stage
Calibrate and reposition the two PIR modules, then add a motion-window feature in firmware.
Use VL53L0X only for a close fixed zone, or evaluate a multizone ToF sensor for ceiling coverage.
Repeat the pilot, collect balanced sessions, train the occupancy model and deploy it with STM32Cube.AI.
Project status | Ahmed Mohamed Abdalla Ahmed | A24KE0429
13
Notes: Source: user-supplied project record and pilot logger results.
MNIST learning reference: https://github.com/Szu-Chi/Implement-MNIST-Handwritten-Digit-Classification-on-MCU
VL53L0X datasheet: https://www.st.com/resource/en/datasheet/vl53l0x.pdf
Multizone ToF option: https://www.st.com/en/imaging-and-photonics-solutions/vl53l5cx